## ProjectSchedule
UniNode
[Company Name] |  |  | Project Start: | 2021-03-01
[Project Lead] |  |  | Today: | 2021-03-12
|  |  | Display Week: | 1 |  |  | 2021-03-01 | [6 empty] | 2021-03-08 | [6 empty] | 2021-03-15 | [6 empty] | 2021-03-22 | [6 empty] | 2021-03-29 | [6 empty] | 2021-04-05 | [6 empty] | 2021-04-12 | [6 empty] | 2021-04-19
 | time axis 2021-03-01 to 2021-04-25
TASK | Θέματα | Ανατέθηκε | Πρόοδος | Έναρξη | Λήξη | DAYS | time axis 2021-03-01 to 2021-04-25
Φάση 1
Ιδέες Υλοποίησης |  | Group | 100% | 2021-03-01 | 2021-03-05
1η Συνάντηση | Brain Storming, Team Bonding, Απόφαση Ιδέας Υλοποίησης | Group | 100% | 2021-03-05 | 2021-03-05 | 1
Brand Name |  | Group | 100% | 2021-03-05 | 2021-03-06 | 2
Μοντέλο Οργάνωσης |  | Group | 50% | 2021-03-05 | 2021-03-06 | 2
Discord Server |  | Στέλιος Νικολαδάκης | 100% | 2021-03-06 | 2021-03-06
2η Συνάντηση Online | Brand Name, Μοντέλο Οργάνωσης | Group | 100% | 2021-03-07 | 2021-03-07
Logo |  | Εμμανουέλα Οικονομοπούλου | 75% | 2021-03-07 | 2021-03-15 | 9
Github Repository |  | Φλωρεντία Αφεντάκη | 100% | 2021-03-07 | 2021-03-07 | 1
3η Συνάντηση | Μοντέλο Οργάνωσης, Ανάθεση Εργασιών | Group | 100% | 2021-03-09 | 2021-03-09
Team-plan-v0.1 |  | Βασιλική Στάμου | 25% | 2021-03-09 | 2021-03-16 | 8
Project-description-v0.1 |  | Εμμανουέλα Οικονομοπούλου | 25% | 2021-03-09 | 2021-03-16 | 8
Project-plan-v0.1 |  | Φλωρεντία Αφεντάκη | 25% | 2021-03-09 | 2021-03-16 | 8
Risk-assessment-v0.1 |  | Στέλιος Νικολαδάκης | 25% | 2021-03-09 | 2021-03-16 | 8
4η Συνάντηση Online | Activities | Group | 0% | 2021-03-12 | 2021-03-12
ΚΑΘΑΡΑ ΔΕΥΤΕΡΑ | Ανάπαυση και γαλήνια περισυλλογή | Group | 0% | 2021-03-15 | 2021-03-15
Τελική Συνάντηση |  | Group | 0% | 2021-03-17 | 2021-03-21
Παραδοτέο 1 |  | Group | 0% | 2021-03-17 | 2021-03-21
Φάση 2
Use-cases-v0.1 |  |  | 0% | 2021-03-21 | 2021-04-07 | 18
Domain-model-v0.1 |  |  | 0% | 2021-03-21 | 2021-04-07 | 18
|  |  | 0% | 2021-03-21 | 2021-04-07 | 18
|  |  | 0% | 2021-03-21 | 2021-04-07 | 18
|  |  | 0% | 2021-03-21 | 2021-04-07 | 18
Φάση 3
Robustness-diagrams-v0.1 |  |  | 0% | 2021-04-07 | 2021-04-25 | 19
Use-cases-v0.2 |  |  | 0% | 2021-04-07 | 2021-04-25 | 19
Domain-model-v0.2 |  |  | 0% | 2021-04-07 | 2021-04-25 | 19
|  |  | 0% | 2021-04-07 | 2021-04-25 | 19
|  |  | 0% | 2021-04-07 | 2021-04-25 | 19
Φάση 4
Sequence-diagrams-v0.1 |  |  | 0% | 2021-04-25 | 2021-05-12 | 18
Domain-model-v0.3 |  |  | 0% | 2021-04-25 | 2021-05-12 | 18
|  |  | 0% | 2021-04-25 | 2021-05-12 | 18
|  |  | 0% | 2021-04-25 | 2021-05-12 | 18
|  |  | 0% | 2021-04-25 | 2021-05-12 | 18
Φάση 5
Class-diagram-v0.1 |  |  | 0% | 2021-05-12 | 2021-05-30 | 19
Project-code-v0.x |  |  | 0% | 2021-05-12 | 2021-05-30 | 19
|  |  | 0% | 2021-05-12 | 2021-05-30 | 19
|  |  | 0% | 2021-05-12 | 2021-05-30 | 19
|  |  | 0% | 2021-05-12 | 2021-05-30 | 19
Φάση 5
Όλες τις εκδόσεις v1.0 |  |  | 0% | 2021-05-30 | 2021-06-06 | 8
Project-code-v1.0 |  |  | 0% | 2021-05-30 | 2021-06-06 | 8
|  |  | 0% | 2021-05-30 | 2021-06-06 | 8
|  |  | 0% | 2021-05-30 | 2021-06-06 | 8
|  |  | 0% | 2021-05-30 | 2021-06-06 | 8
Note on H6: DAYS: This column calculates the duration of the task in calendar days. The duration includes both the Start and End dates.

## Tasks
UniNode
[Company Name]
[Project Lead]
TASKS | Κωδικοποίηση | Προαπαιτούμενα TASKS | Απαισιόδοξη | Κανονική | Αισιόδοξη
Φάση 1
Ιδέα Υλοποίησης | 1 | - | 10 | 6 | 2
Brand Name | 2 | 1 | 3 | 2 | 1
Μοντέλο Οργάνωσης | 3 | - | 10 | 5 | 2
Discord Server | 4 | - | 1 | 1 | 1
Logo | 5 | 2 | 3 | 2 | 1
Github Repository | 6 | 2 | 1 | 1 | 1
Team-plan-v0.1 | 7 | 3 | 7 | 5 | 2
Project-description-v0.1 | 8 | 1 | 7 | 5 | 2
Project-plan-v0.1 | 9 | 7 | 7 | 5 | 2
Risk-assessment-v0.1 | 10 | 7 | 7 | 5 | 2
Παραδοτέο 1 | 11 | 7 8 9 10 | 3 | 2 | 1
Φάση 2
Use-cases-v0.1 | 12
Domain-model-v0.1 | 13
Φάση 3
Robustness-diagrams-v0.1 | 14
Use-cases-v0.2 | 15
Domain-model-v0.2 | 16
Φάση 4
Sequence-diagrams-v0.1 | 17
Domain-model-v0.3 | 18
Φάση 5
Class-diagram-v0.1 | 19
Project-code-v0.x | 20
Φάση 5
Όλες τις εκδόσεις v1.0 | 21
Project-code-v1.0 | 22

## About
SIMPLE GANTT CHART by Vertex42.com
https://www.vertex42.com/ExcelTemplates/simple-gantt-chart.html
© 2018-2019 Vertex42 LLC
About This Template
This template provides a simple way to create a Gantt chart to help visualize and track your project. Simply enter your tasks and start and end dates - no formulas required. The bars in the Gantt chart represent the duration of the task and are displayed using conditional formatting. Insert new tasks by inserting new rows.
Additional Help
Click on the link below to visit vertex42.com and learn more about how to use this template, such as how to calculate days and work days, create task dependencies, change the colors of the bars, add a scroll bar to make it easier to change the display week, extend the date range displayed in the chart, etc.
How to Use the Simple Gantt Chart
► Watch How This Gantt Chart Was Created
More Project Management Templates
Visit Vertex42.com to download other project management templates, including different types of project schedules, Gantt charts, tasks lists, etc.
Project Management Templates
About Vertex42
Vertex42.com provides over 300 professionally designed spreadsheet templates for business, home, and education - most of which are free to download. Their collection includes a variety of calendars, planners, and schedules as well as personal finance spreadsheets for budgeting, debt reduction, and loan amortization.
Businesses will find invoices, time sheets, inventory trackers, financial statements, and project planning templates. Teachers and students will find resources such as class schedules, grade books, and attendance sheets. Organize your family life with meal planners, checklists, and exercise logs. Each template is thoroughly researched, refined, and improved over time through feedback from thousands of users.